# Workflow Roadmap - HGRM SaaS

# Workflow Roadmap — HGRM SaaS

Companion to PRD.md and DATABASE-SCHEMA.md. Work through phases

in order — each depends on the previous one being live. Check off tasks as they're done and

update the Status: line per phase. This file is the single source of truth for "where are we."

Legend: Status: Not Started | In Progress | Blocked | Done

## Phase 0 — Decisions & sign-off

Status: In Progress — proceeded with documented defaults to unblock Phase 1; not yet formally

signed off by the client.

Depends on: nothing

Goal: lock the architecture before any migration exists, so Phase 1+ isn't rework.

☐ Client/stakeholder reads PRD.md and README.md decisions list.

☐ Confirm or revise the 5 decisions already baked into the docs (tenancy model, jurisdiction

auto-scope, per-hotel guests, Hotel Beach Way as Tenant #1, reuse existing Admin shell).

☐ Answer the open questions in README.md: hotel category values, marriage/companion MVP

scope, hotel onboarding flow (self-serve vs. admin-created), NID scan approach.

☑ Decide whether divisions table is in scope for Phase 1 or deferred — **decided: in

scope**, built in Phase 1 (see README.md decision #6).

Definition of done: no open architecture question remains that would change a table shape in

Phase 1–3. Phase 1's table shapes are now built, so any change to decisions 1–5 above would mean

revisiting Phase 2's design before it starts — worth confirming with the client now rather than

after Phase 2.

## Phase 1 — Bangladesh geography reference data

Status: Done (2026-08-01)

Depends on: Phase 0

Goal: districts/upazilas/police stations exist and are seeded, ready for hotels and

users to reference them.

☑ Source a verified Bangladesh administrative dataset — used

nuhil/bangladesh-geocode (cites

bangladesh.gov.bd + Wikipedia; source ids preserved on import so e.g. district id 9 is

reliably Cox's Bazar in every environment).

☑ Migration: divisions table — 2026_08_01_100001_create_divisions_table.php. Kept in

scope (Phase 0 decision resolved: cheap now, expensive to retrofit).

☑ Migration: districts table (+ division_id FK) — 2026_08_01_100002_create_districts_table.php.

☑ Migration: upazilas table (district_id FK) — 2026_08_01_100003_create_upazilas_table.php.

☑ Migration: police_stations table (district_id FK, nullable upazila_id FK) —

2026_08_01_100004_create_police_stations_table.php.

☑ Models: Division, District, Upazila, PoliceStation (app/Models/) with

hasMany/belongsTo relations.

☑ Seeder: Database\Seeders\BdGeographySeeder, idempotent (skips per-table if already

populated), reads JSON snapshots from database/seeders/data/bd-geocode/, wired into

DatabaseSeeder.

☑ Spot-checked via artisan tinker: 8 divisions, 64 districts, 494 upazilas seeded; Cox's

Bazar (district id 9) correctly resolves to Chattagram division and its 9 real upazilas

(Sadar, Chakaria, Kutubdia, Ukhiya, Moheshkhali, Pekua, Ramu, Teknaf, Eidgaon).

☐ Follow-up, not blocking: police_stations currently holds a rural approximation only

(one row per upazila, name mirrored — correct for the large majority of the country,

including Cox's Bazar). Metropolitan police stations (Dhaka Metropolitan Police ~50 thanas,

plus Chattogram/Rajshahi/Khulna/Sylhet/Barishal/Rangpur/Gazipur/Narayanganj Metropolitan

Police) are not seeded — no verified open dataset was found for these. Needed before a

hotel located in one of those metro areas can be registered with a correct police station.

Source an official list (e.g. from the relevant Metropolitan Police website) and extend

BdGeographySeeder before Phase 4 onboards a metro-area hotel.

Definition of done: php artisan migrate --seed produces a complete, queryable geography

tree; no admin UI needed yet (plain Eloquent + artisan tinker verification is enough). ✅ Met —

the one open follow-up (metro police stations) doesn't block Phase 2/3 since neither hotels nor

users require police-station data to exist for districts that don't have metro areas.

## Phase 2 — Hotels & multi-tenancy core

Status: Done (2026-08-01)

Depends on: Phase 1

Goal: the system has a real concept of "hotel," every existing tenant-owned table is scoped

to one, and Hotel Beach Way's existing data is preserved as Tenant #1 with zero functional

regression.

☑ Migration: hotels table — 2026_08_01_100005_create_hotels_table.php. Legal-ID fields

(trade_license_no, owner_name, owner_nid) made nullable and is_primary_site added

during the build — both are real deviations from the original plan, documented in

DATABASE-SCHEMA.md § Phase 2 and

README.md decisions 8–9.

☑ Migration: documents polymorphic table — 2026_08_01_100006_create_documents_table.php.

Table exists; nothing writes to it yet (starts being used in Phase 4/5).

☑ Model: Hotel (+ relations: district, upazila, policeStation, roomTypes, rooms,

customers, bookings, inquiries, users, documents; static primarySite() helper).

☑ Model: Document (+ documentable() morphTo, uploadedBy()).

☑ Migration: additive nullable hotel_id on room_types, rooms, customers,

room_bookings, inquiries, users — 2026_08_01_100007_add_hotel_id_to_tenant_tables.php.

Also fixed customers.phone from a global unique constraint to unique(hotel_id, phone) in

the same migration — required once guests became per-hotel, see schema doc.

☑ Backfill: done inside the same 2026_08_01_100007 migration (not a separate script — it's

a one-off historical operation, not something a fresh install repeats). Hotel Beach Way's

real district/upazila/police station resolved from Phase 1 data, real mobile/email/address

pulled from global_settings; every existing room_types (8), rooms (58), customers

(14), room_bookings (2), inquiries (32), users (3) row backfilled onto it. Verified via

artisan tinker — counts match exactly.

☑ Follow-up migration: 2026_08_01_100008_make_hotel_id_required_on_tenant_tables.php — made

hotel_id NOT NULL on room_types, rooms, customers, room_bookings, inquiries

(raw MODIFY COLUMN, matching this project's existing no-doctrine/dbal convention).

users.hotel_id left nullable as planned.

☑ Added hotel() relation + hotel_id to $fillable on RoomType, Room, Customer,

RoomBooking, Inquiry, and User.

☑ Built the tenant-scoping mechanism — **differs from the original plan, see

DATABASE-SCHEMA.md § Tenant-scoping mechanism

for the full reasoning**:

App\Support\CurrentHotel resolves the scope id (super admin → unrestricted; hotel staff →

their own hotel; **unauthenticated public site/console/queue → the hotel flagged

is_primary_site**, not just "no scoping" as originally sketched — this was the missing

piece that lets the public frontend keep working unchanged).

App\Models\Concerns\BelongsToHotel trait applies the global scope + auto-stamps hotel_id

on create. Applied to RoomType, Room, Customer, RoomBooking, Inquiry.

`User` deliberately excluded from the trait (auth-guard recursion risk discovered during

implementation) — gets the column/relation only, scoped manually per-query when needed.

☑ Audited every Admin/Frontend controller for raw DB::table/DB::select/join queries

against room_types, rooms, customers, room_bookings, inquiries — none found

(ReportController, DashboardController, RoomAvailabilityController all go through

Eloquent), so the global scope's coverage is complete.

☑ Regression check: not a live browser click-through — verified instead via `artisan

tinker` inside a rolled-back DB transaction (created a throwaway second hotel + room type +

hotel-scoped user, confirmed cross-tenant isolation, auto-stamping, and super-admin

unrestricted access, then rolled back with zero persisted test data). Super admin's counts

matched pre-existing totals exactly (8 room types, 58 rooms, etc.), confirming zero

behavior change for Hotel Beach Way staff. A live browser smoke-check of the admin panel

hasn't been done — worth doing before treating this as fully production-verified.

☐ Not done — flagged, not silently skipped: a permanent automated PHPUnit test for tenant

isolation. While verifying this manually, discovered php artisan test /

vendor/bin/phpunit currently runs RefreshDatabase migrations against the **real MySQL

dev database** (no .env.testing, sqlite lines commented out in phpunit.xml) — running

the existing test suite right now would wipe real data. Also, sqlite isn't actually a safe

fix here: this migration set (including two from this phase) uses MySQL-only raw

ALTER TABLE ... MODIFY COLUMN statements sqlite can't run. See

README.md § Known gaps.

Carried forward to Phase 3, which is where the first *required* automated isolation

tests show up — fixing the test DB config is a prerequisite for that task.

Definition of done: Hotel Beach Way operates exactly as before; the schema is ready for a

second hotel to be added without any code change. ✅ Met, with two honest caveats carried forward

rather than hidden: no live browser regression pass yet, and no permanent automated test yet

(blocked on the test-database fix above).

## Phase 3 — RBAC & jurisdiction

Status: Done (2026-08-01)

Depends on: Phase 2

Goal: government role types exist and automatically see the right hotels, with no way to

escalate scope by guessing a URL.

☑ Prerequisite carried over from Phase 2: fixed the test database setup. Root cause was

actually one step earlier than expected — bootstrap/cache/config.php was a **stale cached

config** (from 2026-07-28), so Laravel was ignoring .env entirely and running everything

against frozen values, which is also why .env.testing alone wouldn't have been enough.

Ran php artisan config:clear (safe — deletes a cache file, no data impact) and added

.env.testing pointing at a dedicated hotel-beach-way-testing MySQL database (not

sqlite — confirmed this project's migrations use MySQL-only raw `ALTER TABLE ... MODIFY

COLUMN` statements sqlite can't run). Verified end-to-end by snapshotting real-DB row

counts, running the full RefreshDatabase suite, and re-checking the real DB was

byte-for-byte unchanged afterward.

☑ Bug found and fixed while doing the above: 2026_08_01_100007_add_hotel_id_to_tenant_tables.php

assumed BdGeographySeeder had already run. On a genuinely fresh database — which is

exactly what RefreshDatabase does, and what a first-time php artisan migrate on a new

clone would also do — districts/upazilas/police_stations are empty, so the district/

police-station lookup resolved to null and the hotels insert failed its NOT NULL

constraint. Fixed by having the migration call BdGeographySeeder itself (idempotent, so

free if it already ran) before doing the lookup — makes the migration chain self-sufficient

on php artisan migrate alone, no --seed flag required. This was a real production-

readiness bug in Phase 2's migration, not a test-only artifact — worth knowing if you ever

set up a fresh environment from these migrations.

☑ Migration: roles.scope_type enum column — 2026_08_01_100009_add_scope_type_to_roles_table.php.

☑ Migration: users.district_id, users.upazila_id, users.police_station_id (nullable

FKs) — 2026_08_01_100010_add_jurisdiction_to_users_table.php.

☑ Migration: hotel_user_assignments pivot table — 2026_08_01_100011_create_hotel_user_assignments_table.php.

☑ Added hotel-registration and gov-reports to ModuleRegistry::all() + preemptive

resolveModule() entries (admin.hotels, admin.government) ahead of the Phase 4/6 routes

that will use them — lets the existing Roles UI already grant these modules today.

☑ Built App\Support\HotelAccess::visibleHotelIds(User $user): array — checks

hotel_user_assignments first (exact override), falls back to jurisdiction match on

district_id/upazila_id/police_station_id per the role's scope_type. Wired into

App\Support\CurrentHotel::visibleHotelIds(), which is what

App\Models\Concerns\BelongsToHotel's global scope now calls — **generalized from a single

hotel_id to a whereIn over a set**, so Phase 2's exact same mechanism now serves both

"one hotel" (hotel staff) and "every hotel in my jurisdiction" (government roles) without

two separate code paths.

☑ Route-model-binding guard — turned out to need no new code. Investigated before

building anything: Laravel's implicit route-model binding (e.g. `CustomerController::

show(Customer $customer)) already calls Customer::findOrFail()`, which already respects

the global scope. Once that scope understood jurisdiction sets (previous bullet), a

government/hotel user hitting /admin/customers/{id} for an out-of-scope id already gets a

404 automatically — proven by HotelTenantIsolationTest, not assumed. Deliberately 404 (not

403): a 403 would confirm the record exists at all, which is worse for a system whose whole

point is restricting who can even know a guest stayed somewhere.

☑ Seeder: Database\Seeders\GovernmentRoleSeeder — DC Office (scope_type=district),

UNO Office (scope_type=upazila), Police Admin (scope_type=police_station), each

granted dashboard + gov-reports + customers (view-only). Also sets the existing

super-admin role's scope_type to platform for hygiene (behavior is unaffected either

way — is_super_admin is still the unconditional bypass). Wired into DatabaseSeeder

(after RoleSeeder and BdGeographySeeder, which it depends on).

☑ Seeded 4 test government accounts across 2 districts (dev/QA only — password password

for all): dc.coxsbazar@hgrm.test (DC, Cox's Bazar), dc.dhaka@hgrm.test (DC, Dhaka),

uno.coxsbazarsadar@hgrm.test (UNO, Coxsbazar Sadar upazila),

police.coxsbazarsadar@hgrm.test (Police, Coxsbazar Sadar thana).

☑ Automated isolation tests: tests/Feature/HotelTenantIsolationTest.php, 10 tests

covering hotel-role isolation (including the "misconfigured user with no hotel sees

nothing" fail-closed case), district/upazila/police-station jurisdiction scoping, the

explicit-assignment-overrides-jurisdiction semantic, super-admin unrestricted access, and

unauthenticated public-site scoping — via real HTTP requests

($this->actingAs($user)->get(route('admin.customers.show', $customer))->assertNotFound()),

not just Eloquent queries. All 10 pass; full suite (35 tests) passes; real dev database

confirmed unchanged after the run.

☐ Not done — live browser login QA. The 4 seeded accounts above are ready for a manual

login smoke-check whenever convenient; this session verified correctness via the automated

suite only, not a real browser session.

Definition of done: seeded DC/UNO/Police test accounts each see exactly their jurisdiction's

hotels and nothing else, verified by both manual login and automated tests. ✅ Automated half

solidly met (10 passing isolation tests); manual login QA carried forward as a quick, low-risk

follow-up rather than blocking here.

## Phase 4 — Hotel registration module (Super Admin side)

Status: Done (2026-08-01)

Depends on: Phase 3 (needs hotel-registration module permission wired up)

Goal: Super Admin can onboard a second real hotel end-to-end through the UI — the point

where multi-tenancy stops being theoretical.

☑ Admin\HotelController: index/create/store/edit/update/show/updateStatus/deleteDocument,

gated by hotel-registration module permission (already wired via ModuleRegistry in

Phase 3).

☑ Create/Edit form (shared Admin/Hotels/HotelForm.vue): every PRD § 5.1 field — name,

category (plain text — no fixed classification exists yet, see README open question),

total rooms, trade license/BIN/TIN, owner name/NID, mobile/email/address,

district→upazila→police-station cascading selects (client-side filtering over all

districts/upazilas/police stations passed as props — no extra round-trips), a single hotel

photo (logo), and 4 single-file document uploads (trade license/BIN/TIN/owner NID) +

multi-file gallery photos, all via the documents polymorphic table from Phase 2 — its

first real use.

☑ Inertia pages: Admin/Hotels/{Index,Create,Edit,Show}.vue + shared HotelForm.vue,

following the Rooms/RoomTypes page conventions (DropZone, useForm, table + modal

patterns).

☑ Hotel status control: 4-state changer (pending/active/suspended/rejected) on the Show page,

with a JS confirm() gate before suspending or rejecting.

☑ Sidebar entry added (Hotel Registration, module hotel-registration) — naturally

Super-Admin-only today since no other role has been granted that module.

☑ Added beyond the original plan: a hotel_id select on the existing Users Create/Edit

forms (Admin\UserController + Admin/Users/{Create,Edit}.vue), plus a "Hotel" column on

the Users index. This is *how* "assign a hotel-admin user" actually happens — the original

plan didn't specify where that UI would live; reusing the existing Users screen avoided

building a second, redundant user-management surface on the Hotel page itself. Also created

a Hotel Admin role (scope_type hotel, granted dashboard/bookings/room-management/

customers/inquiries/reports) as the first real non-super-admin hotel-role role.

☑ Created a second real hotel and proved isolation live, not just via automated tests:

"Grand Dhaka Hotel" (id 3, Dhaka district) now exists in the real dev database alongside

Hotel Beach Way, with a real "Grand Dhaka Hotel Admin" user (Hotel Admin role,

hotel_id = 3). No browser automation tool was available in this environment (no

chromium-cli/Playwright), so this was done via genuine HTTP requests (PowerShell

Invoke-WebRequest against a temporary php artisan serve instance, with real CSRF/session

cookie handling — not tinker/Eloquent shortcuts) through the actual login → create-hotel →

create-user → assign-role flow. Confirmed live: the new hotel admin's dashboard loads

(200), a direct request for Hotel Beach Way's real customer record returns 404, and

requesting the Hotel Registration screen (a module they weren't granted) redirects them

away (302) — the exact three checks the Phase 3 automated suite makes, now reproduced

against real production-adjacent data. The scripting-only temporary super-admin account

used to drive the HTTP flow was deleted afterward; the real hotel and its real admin user

were kept.

☑ Backend also covered by 7 new automated tests, tests/Feature/HotelRegistrationTest.php

(permission gating, file upload + replacement + deletion, duplicate trade-license

rejection, status changes, and the assign-then-isolate flow through the real

UserController::store endpoint). Full suite: 42 tests passing.

☐ Not done — live visual browser check. No headless browser tool (chromium-cli,

Playwright) was available in this environment to click through the actual rendered Vue UI

(cascading selects behaving correctly in the DOM, DropZone previews, modal interactions).

The backend behind every one of those interactions is verified (above); the UI code

compiles cleanly (npm run build succeeded, HotelForm-*.js present in the build output).

Worth a quick manual look next time this is opened in an actual browser.

Definition of done: two independently operating hotels exist in the system, each manageable

only by their own staff, both visible to Super Admin. ✅ Met and verified live — see above.

## Phase 5 — Guest / customer KYC expansion

Status: Done (2026-08-02)

Depends on: Phase 2 (needs hotel_id on customers); independent of Phases 3–4

Goal: the full guest KYC dataset from PRD § 5.3 is capturable and stored per hotel.

☑ Migration: new customers columns — 2026_08_02_100001_add_kyc_fields_to_customers_table.php

(father/mother name, gender, DOB, occupation, emergency contact, present/permanent address,

district/upazila/police-station, post code, birth certificate number, driving license

number, foreign-guest fields, couple/marriage fields, is_flagged/flagged_note).

☑ Updated Customer model $fillable/casts (date + boolean casts for the new columns);

added district()/upazila()/policeStation()/documents() relations.

☑ **Decision made during implementation — KYC completion lives on a new

Admin/Customers/Edit.vue, not the booking-creation form.** The roadmap left this open

("wherever guest details are captured"). Bookings still capture only

name/phone/email/nationality/document quickly at reservation time (unchanged,

RoomBookingController::resolveCustomer() untouched); the full ~25-field PRD § 5.3 KYC

form is a dedicated front-desk registration screen, matching how hotels actually complete

compliance paperwork at physical check-in rather than at the moment of reservation. Sections

match PRD § 5.3 exactly: Personal / Identity / Foreign Guest / Marriage / Photo / Documents.

☑ Conditional required-field validation via required_if: visa_number/arrival_date_bd

required when is_foreign_guest; spouse_name required when is_couple.

☑ Document uploads wired to the documents table with exactly the categories from the schema

doc (nid_front, nid_back, passport_scan, visa, marriage_certificate, guest_photo,

other) via a new shared App\Support\DocumentUploader (extracted from Phase 4's

HotelController — same single-file-replace / multi-file-append logic, now used by both

controllers instead of duplicated). Storage path guessability confirmed the same way as

Phase 4 (random hashed filenames, no directory listing).

☑ Guest photo: new shared WebcamCapture.vue component (getUserMedia + canvas snapshot →

File) as one path, existing DropZone upload as the other — a toggle switches between

them, both feeding the same guest_photo_doc form field/documents category so the backend

doesn't care which path was used.

☑ Police-only is_flagged/flagged_note: User::canManagePoliceFlag() (super admin or

scope_type = police_station) gates this in Admin\CustomerController — the fields are

stripped from the Inertia response via makeHidden() for unauthorized roles (not just

hidden in Vue) *and* silently ignored on write if a non-police request includes them.

Verified by CustomerKycTest asserting the keys are actually absent from the response

props, not just unrendered.

☑ **Also done (not separately called out in the original checklist, but required for the

Roles UI to make any of this grantable)**: added edit/delete to the customers module's

allowed actions in ModuleRegistry — it was ['view']-only before, which meant no role

(other than super admin) could ever have been granted permission to edit a guest record

even after this screen existed.

☑ Real bug found and fixed while manually verifying over live HTTP (not caught by the

first round of automated tests): Inertia's forceFormData — required here because the form

has file uploads — serializes JS checkbox booleans through FormData as the literal strings

"true"/"false", and Laravel's boolean validation rule actually rejects the string

"false" outright. Every real update silently failed validation whenever a checkbox was

left unchecked. Fixed by normalizing with $request->boolean() before validation; added a

dedicated regression test (`test_update_succeeds_with_string_boolean_values_matching_real_

form_submissions`) using raw string values specifically, since the other tests used

PHP-native booleans and would never have caught this. Re-verified live afterward against the

real dev database.

☑ Automated tests: tests/Feature/CustomerKycTest.php, 8 tests (conditional validation,

document category correctness, the police-flag gating in both directions, and the

boolean-string regression above). Full suite: 50 tests passing.

☑ Verified live against the real dev database (same pattern as Phase 4 — genuine HTTP

requests via a temporary artisan serve, reusing the real "Grand Dhaka Hotel Admin" account

from Phase 4 rather than creating a new throwaway account): opened the edit page for a real

guest at Grand Dhaka Hotel (200), confirmed a Hotel Beach Way guest's edit page 404s for this

user (cross-tenant isolation still holds for the new routes), and successfully updated the

real guest record end to end.

☐ Not done — live visual browser check, same recurring caveat as Phase 4: no headless

browser tool available in this environment. npm run build succeeds; the webcam-vs-upload

toggle and cascading location selects are unverified visually.

Definition of done: a front-desk user can capture a complete guest record matching every

field in PRD § 5.3, for both domestic and foreign guests, with documents attached. ✅ Met and

verified live.

## Phase 6 — Government reports & dashboards

Status: Done (2026-08-02)

Depends on: Phases 3 (jurisdiction scoping) and 5 (KYC fields to report on)

Goal: every report/dashboard listed in PRD § 5.4–5.5 works, correctly scoped, exportable.

☑ **Decision made during implementation — extended DashboardController, not a new

controller.** DashboardController::index() now branches on the current user's role

scope_type: district/upazila/police_station renders the new government dashboard;

everyone else (hotel roles, super admin) sees the existing hotel-operations dashboard

unchanged. Same route (admin.dashboard), same dashboard module permission (already

granted to government roles by GovernmentRoleSeeder) — no new route needed.

☑ New App\Support\GovernmentStats — shared occupancy aggregation (per-hotel current

guests/today's check-in/check-out, 30-day trend) used by *both* the government dashboard

and the standalone Hotel-wise report, so that number is computed in exactly one place.

Relies entirely on the existing tenant/jurisdiction global scope for correctness (see

note below) — no manual hotel_id IN (...) filtering anywhere in this class.

☑ Admin\GovernmentReportController: Hotel-wise report, Guest report (also serves

Date-wise and Foreign Guest via query-param filters/preset sidebar links rather

than 3 separate near-identical screens), Nationality report, NID search — all

jurisdiction-scoped.

☑ PDF export via existing barryvdh/laravel-dompdf, new admin.government.pdf blade view

(couldn't reuse admin.reports.pdf — it hardcodes "Hotel Beach Way" in the title, wrong

for a report spanning multiple hotels).

☑ Excel/CSV export: plain streamed CSV, no new dependency, as planned.

☑ Inertia pages: `Admin/Government/{Dashboard,HotelReport,GuestReport,Nationality,

NidSearch}.vue + shared ExportLinks.vue` component.

☑ Sidebar entries under a new "Government Reports" section, gated by gov-reports — added

query-param support (route(name, query)) to SidebarNavItem.vue, which didn't exist

before and would have silently dropped the Date-wise/Foreign-Guest preset filters.

☑ Police-only flagged-guest filter on the Guest report, gated by the same

User::canManagePoliceFlag() from Phase 5.

☑ Correctness note worth keeping: Customer carries the tenant global scope directly,

so Customer:: queries (nationality report, NID search) are automatically scoped with no

extra code. BookingRoom does not carry it (by Phase 2 design — it inherits scope via

its parent booking); every query against it here goes through

whereHas('booking', ...) or eager-loads booking, and since RoomBooking *is* scoped,

the subquery/join is what actually restricts results. Get this pattern wrong (e.g. filter

BookingRoom directly without touching booking) and jurisdiction scoping silently stops

applying — automated tests exist specifically to catch that class of regression.

☑ Automated tests: tests/Feature/GovernmentReportsTest.php, 8 tests — jurisdiction scoping

on the hotel report, guest report, and NID search; confirms government roles are actually

blocked from admin.reports.* (hotel financials); confirms the dashboard branch picks the

right component for government vs. super-admin accounts. Full suite: 58 tests passing.

☑ Verified live against the real dev database (same practice as Phases 4–5): logged in

as the real seeded dc.coxsbazar@hgrm.test account, confirmed the dashboard renders the

government component with correctly scoped stats, the Hotel-wise report shows Hotel Beach

Way but not Grand Dhaka Hotel (Dhaka — different jurisdiction), admin.reports.income

redirects away, NID search finds an in-jurisdiction guest but not Grand Dhaka Hotel's, and

both CSV and PDF export endpoints return real, correctly-scoped output (verified byte

count/content-type, not just status code).

☐ Not done — live visual browser check, same recurring caveat as Phases 4–5.

Definition of done: every report type in PRD § 5.4 renders correct, jurisdiction-scoped data

and exports to both PDF and CSV. ✅ Met and verified live.

## Phase 7 — Isolation testing, audit logging, rollout

Status: Done (2026-08-02)

Depends on: Phases 1–6 complete

Goal: confidence this is safe to hand to real government offices, plus the compliance

audit trail expected of that positioning.

☑ Full regression pass on Hotel Beach Way's original functionality. **Found a real gap while

doing this**: the booking flow — the app's original, core feature — had *zero* automated

test coverage before this, despite six phases of changes touching every model it depends on

(Customer/RoomBooking/BookingRoom all gained hotel_id + global scopes). Added

tests/Feature/BookingFlowRegressionTest.php (public availability check, public booking

creation, admin manual booking creation, all with Mail::fake() — this environment's mail

config routes to a real SMTP server even from tinker/local testing, so any booking-flow

check that skips Mail::fake() risks sending real email to real inboxes) rather than just

asserting nothing broke. Also caught and fixed two Phase 4/5 tests that still referenced the public

disk after this phase's document-storage change (see below) — HotelRegistrationTest and

CustomerKycTest — and cleaned up real orphaned files those tests had written to

storage/app/ before the fix.

☑ Expanded Phase 3/6 isolation tests: a hotel-role account has zero permission on any

admin.government.* route (added to GovernmentReportsTest); a government user cannot use

the Guest report's ?hotel_id= filter to see another jurisdiction's data (the filter ANDs

onto an already-scoped query, so this was safe by construction — now proven, not assumed).

☑ Migration + model: audit_logs, App\Models\AuditLog, and a new App\Support\AuditLogger

helper — logs only super-admin/government-scoped access (viewed_guest,

viewed_guest_document, searched_nid, exported_report), deliberately not routine

hotel-staff activity. Wired into CustomerController::show/edit, DocumentController::show

(guest documents only), and GovernmentReportController's NID search and both export

methods.

☑ Security pass found a real gap, not just confirmed one was absent. The documents

table (Hotel legal docs + all guest KYC documents from Phases 4–5) was stored on the

public disk — served directly by the webserver with zero authentication. Random

hashed filenames made paths hard to *guess*, which is not the same as "not publicly

reachable without auth." Fixed by moving all documents-table storage to the local disk

(storage_path('app'), not web-accessible) and adding Admin\DocumentController::show,

which re-checks module permission *and* tenant/jurisdiction scope (via Customer::find()

respecting the same global scope everything else relies on) on every request. Confirmed

live: the old direct path is unreachable, an in-jurisdiction government account gets the

file, an out-of-jurisdiction one gets 404, unauthenticated gets redirected to login. Hotel

logo and future public hotel marketing photos were deliberately left on the public disk

— see DATABASE-SCHEMA.md § Phase 7

for why that split is fine. Confirmed government accounts still can't reach admin.reports.*

(unchanged from Phase 6).

☑ docs/hgrm-saas/GOVERNMENT-USER-GUIDE.md — what each role sees day to day, plus the

go-live checklist for turning a seeded test government account into a real one.

☑ Go-live checklist written (in the guide above) rather than executed — seeding *real* DC/UNO/

Police accounts for specific real offices is a client rollout decision, not something to do

unprompted. The 4 Phase 3 test accounts remain clearly test-only (@hgrm.test emails, shared

password) and are documented as not-for-production in the guide.

☑ Automated tests: tests/Feature/DocumentSecurityTest.php (8 tests — auth required, tenant/

jurisdiction scoping on document access, hotel-registration permission gating, audit logging

fires for government/platform accounts and not for routine staff), plus the isolation/

regression additions above. Full suite: 71 tests passing.

☑ Verified live against the real dev database (same practice as every prior phase):

uploaded a real trade-license PDF to the real Grand Dhaka Hotel and a real NID scan to the

real guest "Rafiq Ahmed," confirmed the files landed under storage/app/ (not

public/storage/), confirmed dc.dhaka@hgrm.test (in-jurisdiction) can view the NID scan

and dc.coxsbazar@hgrm.test (out-of-jurisdiction) gets 404, and confirmed a real

audit_logs row was written with the correct category metadata. **Also found and fixed a

real environment issue while doing this**: a stale duplicate artisan serve process left

over from earlier verification sessions was silently intercepting some requests, and two of

the four seeded government test accounts' passwords had drifted from the documented

password value at some point in this session — both fixed (killed the stale process; reset

the two accounts via tinker, matching GovernmentRoleSeeder's intended state).

Definition of done: isolation is verified by tests (not just manual spot-checks), every

sensitive-data access is logged, and real government accounts are seeded and confirmed working.

✅ Isolation and audit logging fully met and verified live. Real (non-test) government account

seeding is deliberately left as a client go-live decision — the checklist for it is written and

ready in GOVERNMENT-USER-GUIDE.md.